## Product Roadmap
Phase | Task | Sub-Task | Est. Start Week (July 1, 2025 = Week 1) | Est. End Week | Duration (Weeks) | Description | Key Deliverables | Dependencies | Primary Tools | Owner
Phase 1: Discovery & Definition |  |  | 1 | 8 | 8 | Understand and validate the problem, market, and initial user needs. | Validated Problem Statement, "Gap & Need" Dashboard, User Personas, Market Analysis, Business Model Canvas. | N/A
| 1.1 Problem & Needs Validation | 1.1.1 Project Kick-off & Alignment | 1 | 1 | 1 | Formal project initiation, stakeholder alignment on initial problem statement & goals. | Kick-off Meeting Minutes, Initial Problem Statement. | N/A | Confluence/Notion, Miro/FigJam | PM, BA
|  | 1.1.2 User Research Planning | 1 | 2 | 2 | Define research objectives, target participant profiles, interview guides, and survey questions. | Research Plan, Interview Guides, Survey Draft. | 1.1.1 | Confluence/Notion, Qualtrics/SurveyMonkey | BA, UX
|  | 1.1.3 Data Collection (Interviews & Surveys) | 2 | 4 | 3 | Conduct qualitative interviews and distribute surveys to students, professors, administrators, and trainers. | Raw Interview Transcripts, Survey Responses. | 1.1.2 | UserTesting.com/Lookback, Qualtrics/SurveyMonkey | BA, UX
|  | 1.1.4 Data Synthesis & Pain Point Mapping | 4 | 5 | 2 | Analyze raw data to identify common pain points, "Jobs-to-be-Done" , and desired outcomes. | Affinity Maps (Miro), JTBD Framework, Initial Problem Validation Summary. | 1.1.3 | Miro/FigJam, NVivo (optional) | BA, UX
| 1.2 Market & Competitive Analysis | 1.2.1 Market Sizing Research | 2 | 4 | 3 | Research Total Addressable Market (TAM) , Serviceable Available Market (SAM) , and Serviceable Obtainable Market (SOM) for EdTech/Adaptive Learning. | Market Sizing Report (TAM, SAM, SOM). | N/A | Gartner, HolonIQ , Zion Market Research, Google Sheets | BA
|  | 1.2.2 Competitive Landscape Analysis | 3 | 5 | 3 | Identify and analyze direct , indirect , and phantom competitors; assess their strengths, weaknesses, and market positioning. | Competitive Matrix, Competitor Profiles. | N/A | SimilarWeb, Confluence/Notion | PM, BA
| 1.3 Insights Consolidation & Modeling | 1.3.1 User Persona Development | 5 | 6 | 2 | Create detailed user personas based on validated research findings, including goals, pain points, behaviors, and demographics. | Detailed User Personas. | 1.1.4 | Xtensio, Confluence/Notion | UX, BA
|  | 1.3.2 Business Model Canvas Development | 6 | 7 | 2 | Collaboratively define MyPal's key components: value propositions , customer segments , revenue streams , cost structure , etc.. | Completed Business Model Canvas. | 1.1.4, 1.2.1, 1.2.2 | Miro/FigJam, Confluence/Notion | PM, BA
|  | 1.3.3 "Gap & Need" Dashboard Creation | 7 | 8 | 2 | Build interactive dashboard in Google Sheets to visually present the validated problems (gap) and articulated demands (need). | Live Google Sheets Dashboard. | 1.1.4, 1.3.1 | Google Sheets | BA
Phase 2: Ideation & Design |  |  | 9 | 21 | 13 | Define MyPal's core solution, prioritize features, and design the user experience for the MVP. | Refined Solution, MVP Scope, Prioritized Backlog, User Stories, UX Designs, Prototype. | Phase 1 Complete
| 2.1 Solution Definition & Prioritization | 2.1.1 Solution Alignment Workshop | 9 | 9 | 1 | Present dashboard insights, align stakeholders on MyPal's refined core solution statement and high-level MVP goals. | Refined MyPal Core Solution Statement. | 1.3.3 | Confluence/Notion, Miro/FigJam | PM, BA, UX, Tech
|  | 2.1.2 MVP Definition Workshop | 9 | 10 | 2 | Collaboratively identify essential features for MVP (must-haves to deliver core value). | Agreed-upon MVP Feature List. | 2.1.1 | Miro/FigJam, Confluence/Notion | PM, BA, UX, Tech
|  | 2.1.3 High-Level Backlog Creation | 10 | 11 | 2 | Translate MVP features into Epics/Features in the product backlog tool. Add non-MVP features for future consideration. | Initial Product Backlog (Epics/Features). | 2.1.2 | Jira/Azure DevOps | PM
|  | 2.1.4 Feature Prioritization (RICE/ICE) | 11 | 12 | 2 | Objectively score and rank all features in the backlog based on Reach, Impact, Confidence, and Effort. | Prioritized Product Backlog. | 2.1.3 | Productboard/Aha!, Jira/Azure DevOps | PM, Tech
| 2.2 Requirements Detailing | 2.2.1 High-Level User Story Drafting | 12 | 13 | 2 | Draft initial user stories for all MVP features from the user's perspective. | High-Level User Stories for MVP. | 2.1.4 | Jira/Azure DevOps | BA
|  | 2.2.2 Detailed Functional Requirements | 13 | 16 | 4 | Elaborate on high-level user stories, defining specific functional behaviors, business rules, and data requirements for each MVP feature. | Detailed Functional Requirements (User Stories with Acceptance Criteria). | 2.2.1 | Jira/Azure DevOps, Confluence/Notion | BA
|  | 2.2.3 Non-Functional Requirements | 14 | 15 | 2 | Define performance, security, scalability, usability, and other non-functional requirements for the MVP. | Non-Functional Requirements Document. | 2.1.2 | Confluence/Notion | BA, Tech
| 2.3 User Experience (UX) Design | 2.3.1 Information Architecture & User Flows | 12 | 14 | 3 | Map out the overall structure of MyPal and how users will navigate through key tasks. | Site Map, User Flow Diagrams. | 2.1.2 | Miro/FigJam | UX, BA
|  | 2.3.2 Wireframing & Low-Fidelity Mockups | 14 | 16 | 3 | Create skeletal layouts and basic visual representations of MyPal's screens. | Low-Fidelity Wireframes. | 2.3.1 | Figma/Sketch/Adobe XD | UX
|  | 2.3.3 High-Fidelity Mockups & UI Design | 16 | 19 | 4 | Develop detailed visual designs, including branding, color palettes, and interactive elements. | High-Fidelity Mockups, UI Style Guide. | 2.3.2 | Figma/Sketch/Adobe XD | UX
|  | 2.3.4 Interactive Prototyping | 19 | 20 | 2 | Create clickable prototypes to simulate the user experience for key MVP flows. | Clickable Prototype. | 2.3.3 | Figma (Prototyping), InVision | UX
|  | 2.3.5 Prototype Usability Testing | 20 | 21 | 2 | Conduct usability tests with target users to gather feedback on design and user flows. | Usability Test Report, Design Iteration Recommendations. | 2.3.4 | UserTesting.com, Lookback | UX, BA
Phase 3: Development & Testing |  |  | 22 | 47 | 26 | Build a robust, high-quality MVP of MyPal, ensuring it meets functional and non-functional requirements. | Functional MyPal MVP, Integrated AI/ML, Integrated LMS, Test Reports, Pilot Feedback. | Phase 2 Complete
| 3.1 Agile Development Sprints | 3.1.1 Sprint Planning (Initial) | 22 | 22 | 1 | Plan the first development sprint, breaking down user stories into tasks. | Sprint Backlog, Sprint Goals. | 2.2.2, 2.2.3, 2.3.3 | Jira/Azure DevOps | Dev, PM, BA, QA
|  | 3.1.2 Development Sprints (Iterative) | 22 | 43 | 22 | Execute development sprints, including daily stand-ups, sprint reviews, and retrospectives. | Working Software Increments. | 3.1.1 | Jira/Azure DevOps, GitHub/GitLab, Slack/MS Teams | Dev, PM, BA, QA
| 3.2 Core Feature Development | 3.2.1 Backend Development (AI/ML) | 22 | 40 | 19 | Develop server-side logic, database, and AI/ML models for personalization, adaptive assessment, and content recommendations. | Backend APIs, Trained AI Models. | 2.2.2, 2.2.3 | AWS Sagemaker/Google AI Platform/Azure ML, GitHub/GitLab | Dev
|  | 3.2.2 Frontend Development | 23 | 44 | 22 | Implement user interface based on approved designs, ensuring responsiveness and performance. | Functional UI. | 2.3.3 | GitHub/GitLab | Dev
|  | 3.2.3 LMS Integration Development | 24 | 41 | 18 | Develop APIs and connectors for seamless data exchange with target LMS platforms (Canvas, Blackboard, Moodle). | Working LMS Integrations. | 2.2.2, 2.2.3 | Postman, GitHub/GitLab | Dev
| 3.3 Quality Assurance (QA) | 3.3.1 Test Plan Development | 25 | 26 | 2 | Create comprehensive test plans (functional, integration, performance, security) based on requirements. | Test Plan Document. | 2.2.2, 2.2.3 | TestRail, Confluence/Notion | QA, BA
|  | 3.3.2 Test Case Execution & Bug Tracking | 26 | 45 | 20 | Execute test cases, identify and log bugs, re-test fixes. | Test Reports, Bug Log. | 3.2.1, 3.2.2, 3.2.3 | TestRail, Jira/Azure DevOps | QA
| 3.4 Pilot Testing | 3.4.1 Alpha/Internal Testing | 40 | 42 | 3 | Internal testing by MyPal team members and select friendly users to catch major issues. | Internal Test Report, Initial Bug Fixes. | 3.2.1, 3.2.2, 3.2.3 (Initial Dev Complete) | Jira/Azure DevOps | QA, Dev
|  | 3.4.2 Beta Program Setup & Recruitment | 42 | 44 | 3 | Define beta goals, recruit pilot institutions/users, set up feedback channels. | Beta Program Plan, Pilot User List. | 3.4.1 | Intercom/Zendesk, Qualtrics | PM, Marketing
|  | 3.4.3 Beta Testing & Feedback Collection | 44 | 47 | 4 | Run beta program, collect detailed feedback, monitor performance. | Beta Test Report, Prioritized Feedback Backlog. | 3.4.2 | Intercom/Zendesk, Productboard/Aha! | PM, BA, QA
Phase 4: Launch & Initial Growth |  |  | 48 | 60 | 13 | Successfully launch MyPal to the target market and acquire initial users, proving product-market fit. | Detailed GTM Plan, Marketing Assets, Sales Training, Public MyPal Platform, Initial Client Acquisition. | Phase 3 Complete
| 4.1 Go-to-Market Strategy | 4.1.1 Pricing & Packaging Finalization | 48 | 49 | 2 | Finalize pricing models (licensing, subscription tiers) and feature packaging. | Pricing Model Document. | 1.3.2, 2.1.4 | PM, Sales
|  | 4.1.2 GTM Plan Development | 48 | 50 | 3 | Develop comprehensive launch plan, including target audience, messaging, channels, and KPIs. | GTM Plan Document. | 4.1.1 | Productboard/Aha!, Confluence/Notion | PM, Marketing
|  | 4.1.3 Marketing Asset Creation | 49 | 52 | 4 | Develop website content, brochures, demo videos, social media campaigns, and ad creatives. | Marketing Website, Collateral. | 4.1.2 | WordPress/Webflow, Adobe Creative Suite | Marketing
|  | 4.1.4 Sales & Support Training | 50 | 51 | 2 | Train sales team on product features, value proposition, and competitive differentiation; train support team on common issues. | Sales Playbook, Support Training Manuals. | 4.1.3 | Salesforce, Confluence/Notion | PM, Sales, Support
| 4.2 Launch Execution | 4.2.1 Pre-Launch Marketing Blitz | 52 | 53 | 2 | Execute initial marketing campaigns to build awareness and generate leads. | Lead Generation Reports. | 4.1.3 | Marketo/Pardot/HubSpot | Marketing
|  | 4.2.2 Public Launch/Targeted Rollout | 53 | 53 | 1 | Official release of MyPal to the public or targeted institutional clients. | Publicly Available MyPal Platform. | 4.2.1, 3.4.3 (Beta Feedback Integrated) |  | PM, Dev, Marketing
|  | 4.2.3 Initial User Onboarding & Support | 53 | 56 | 4 | Provide dedicated support for early adopters, ensuring smooth onboarding and addressing initial issues. | Onboarding Success Rate, Initial Support Tickets. | 4.2.2 | Intercom/Zendesk | Support, Customer Success
Phase 5: Post-Launch Optimization & Scale |  |  | 61 | Ongoing | Ongoing | Continuously improve MyPal based on user feedback and data, expand features, and scale adoption. | Updated Roadmap, New Feature Releases, Improved Engagement/Outcomes, Scaled Adoption. | Phase 4 Complete
| 5.1 Continuous Monitoring & Feedback | 5.1.1 KPI Monitoring & Reporting | 61 | Ongoing | Ongoing | Continuously track key performance indicators (Engagement Time , Course Completion Rate , Dropout Rate, NPS). | Live BI Dashboards. | 4.2.2 | Amplitude/Mixpanel/GA4, Tableau/Power BI/Looker | PM, BA, Data
|  | 5.1.2 User Feedback Collection | 61 | Ongoing | Ongoing | Implement ongoing surveys, in-app feedback, and conduct regular user interviews. | Continuous Feedback Stream. | 4.2.3 | Intercom/Zendesk, Qualtrics | PM, BA, UX
|  | 5.1.3 A/B Testing & Experimentation | 62 | Ongoing | Ongoing | Run experiments to optimize features, onboarding flows, and content delivery. | Experiment Reports. | 5.1.1 | Optimizely, Google Optimize | PM, Data
| 5.2 Product Iteration & Expansion | 5.2.1 AI/ML Model Refinement | 61 | Ongoing | Ongoing | Continuously retrain and refine AI/ML models based on new data and performance. | Improved AI Accuracy/Effectiveness. | 5.1.1 | AWS Sagemaker/Google AI Platform/Azure ML | Dev (Data Science)
|  | 5.2.2 Feature Enhancement & New Development | 62 | Ongoing | Ongoing | Prioritize and develop new features (e.g., gamified elements , advanced study pods ) based on feedback and market needs. | Regular Feature Releases. | 5.1.2, 5.1.3 | Jira/Azure DevOps | PM, Dev
|  | 5.2.3 Content Expansion & Curation | 63 | Ongoing | Ongoing | Continuously add new educational content and ensure its quality and relevance. | Expanded Content Library. | 5.1.2 | Content Management System | Content Team
| 5.3 Scaling & Growth | 5.3.1 Infrastructure Scaling | 61 | Ongoing | Ongoing | Monitor system performance and scale infrastructure to support growing user base. | Scaled Infrastructure. | 5.1.1 | Cloud Provider Consoles (AWS, GCP, Azure) | Dev (Ops)
|  | 5.3.2 Partnership Development | 64 | Ongoing | Ongoing | Explore and establish partnerships with new LMS vendors , content providers , and educational organizations. | New Partnership Agreements. | 5.1.1 | Salesforce | PM, Sales
|  | 5.3.3 Market Expansion | 68 | Ongoing | Ongoing | Plan and execute expansion into new geographic regions or customer segments (e.g., specific corporate training niches ). | Market Expansion Strategy. | 5.1.1, 5.1.2 | PM, Marketing